## Feature_List_Example,_Template
1960s MainQuad Feature List:
Reference # | Feature Name | Top Level Description | Priority | Difficulty | Time To Implement | Risk | Comments
F001 | NUC interaction | Primary interaction system | High | High | High | Might need audio support | Main feature of the project, need to be done ASAP
The script should follow the history to keep immersion
Should be matched with correct persona
Good NUC model is hard to get
F002 | Movement | We want to support a free walking system | High | Low | Low | Possibly glicth caused by walk freely | We may be implement transport movement if big issue occured
F003 | Buildings | Rebuild 1960s Main Quad building | Med | Med | High | The quality of Building depends on the model we are given by sponsor | We only implement rough building layout in phase one
|  | Possible introduction of buidlings implemented |  |  |  | The information of 1960s main quad building distribution is hard to find
F004 | Persona Change | Ability to change player's character | High | Low | Med | The change of persona can only be told by change of UI, the possible risk is NUC interaction implementation | It is undecidable whether the change should be made only in the main hall area.
F005 | Audio | NUC's audio design | Low | Med | Low | Mainly depends on source provided by sponsor.
Environmental audio design
F006 | Main Hall | PreGame scene | Med | Low | Low |  | may be the only place to change persona

## Tech_Design_Examples,_Template
Ver 1.1 | Modified 9/11/2018
Ref # | System Name | Feature Supported | Feature Specifics | Priority | Difficulty | Risk | Time Estimation | Comments
F001 | Traversal
F001a |  | Camera |  | High | Med | Low
|  |  | Controller based |  |  |  |  | The movement of camera depends on controller input
|  |  | Headset based |  |  |  |  | Camera view move depends on headset motioni
F001b |  | Controls |  | High | Low | Med |  | Implemented At First
Walk
|  |  | Transport |  |  |  |  | To Be determined
F001c |  | Determine Player Location(QUAD MAP) |  | Low | Low | Low
F002 | NUC AI
F002a |  | Interaction |  | High | High | Med
|  |  | Different events based on persona |  |  |  |  | Player's persona can trigger unique conversation.
|  |  | Triggered interactioni events |  |  |  |  | Conversation should be activated only by click the shown button.
|  |  | Conversation System |  |  |  |  | Conversation tree
F002b |  | Movement |  | Low | Med | Med
|  |  | NUC might move spontaneously |  |  |  |  | Only implement movable NUC if timing is good.
F003 | Environment
F003a |  | Buildings |  | High | Med | Low
|  |  | Texture |  |  |  |  | The looking of the buildings should reflect the feature of original buildings back 1960s
|  |  | History |  |  |  |  | Player might be able to check the history of the buildings
|  |  | Introduction |  |  |  |  | Player could be able to know the introdution of the buildings.
F003b |  | Audio |  | Med | Med | Low |  | implemented mainly provided by sponsors
NUC's background audio
NUC's conversation audio
Environmental audio

## Milestones_Example,_Template
Project: | Your Project name goes here
Date | Milestone | Task | Assets to be created | % Complete | Comments
2019-10-11 | Design I
|  | Create Vision Canvas | None | 100
|  | Create World Discription | None | 100
|  | Create High Level Game Loop | None | 100
2019-10-27 | Design II
|  | Create Tech Design Doc | None
|  | Create QA Test Plan | None
|  | Create Milestones | None
|  | Create Feature List | None
2019-11-10 | Feature I
|  | Basic Vintage Quad Enviroment |  |  | Assigned to Hongxuan Chen and Xinyu Liu
True to Size Quad layout
Placeholders for buildings
|  | Basic UI System |  |  | Assigned to Yuefeng He and Jiaming Zhang
Start Menu
In-game UI
|  | Basic Movement System |  |  | Assigned to Yuefeng He and Jiaming Zhang
Teleportation Movement
2019-11-17 | Feature II
Persona Change System
|  |  | Intereacting Area for Change(The Main Hall) |  | Assigned to Hongxuan Chen and Xinyu Liu
|  |  | Mirror showing different persona in the Main Hall |  | Assigned to Hongxuan Chen and Xinyu Liu
|  |  | Designing personas |  | Assigned to Yuefeng He and Jiaming Zhang
|  |  | Verying UI style matching different personas |  | Assigned to Yuefeng He and Jiaming Zhang
2019-11-24 | Feature III | Immersive Audio |  |  | Assigned to Hongxuan Chen and Xinyu Liu
Background Audio
Intereaction Aduio
Enviroment Audio
|  | Sample NUC |  |  | Assigned to Yuefeng He and Jiaming Zhang
NUC AI System
NUC Intereaction System
NUC Conversation System
Insert New Dates | Insert new Milestones | Insert New Tasks | Insert New Asset Lists |  | Add new rows to include new milestones, add as many as you need
Some Date | Vertical Slice |  |  |  | First attempt at showing what game play and look will be

## QA_Test_Plan_Example,_Template
QA Test Plan |  | Project:60s Main Quad
Date | Build # | Tester Name
2019-01-14
Test # | Unit/Feature | Item | Success/Fail
1 | Main Screen
1a |  | Game Loads properly to Main Screen
1b |  | UI elements change correctly as persona changes
1c |  | Choosing <Start Game> functions correctly by placing the player in the game at main hall
1d |  | Choosing <Exit Game> functions correctly closing out the game cleanly and places the player back in the platform interface
1e |  | Choosing <Settings> functions correctly by taking you to the Player Setting System
2 | Main Hall
2a |  | Change Persona functioned normally
2b |  | Teleport to the main quad scene normally
3 | NUC
2a |  | NUC can normally trigger the events when press the given botton (interaction)
2b |  | NUC can have different conversations depends on persona
3 | Environment
3a |  | Player can freely wander
3b |  | The triggered area is functioned correctly
3c |  | Buildings appearance looks normal

## Copy of Vision_Canvas_Template
High Level Vision Canvas
U of I Quad VR Experience(late 60s, early 70s)
Inspirations (note what is it inspiring) | Genre (ex: 3rd Person) | Core Pillars (in the form "User can...") | Core Systems (ex: Save/Load or Combat) | User Experience (the emotion elicited)
Sponsor project | First Personal | The user will be able to move around the environment | Dialogue Tree | -Immersion in the late 60s and early 70s U of I Quad
Reflecting Real Life in late 60s and early 70s in the United States | Educational social history simulator | The user will be able to choose highlighted interactions available on the quad. | Teleport Movement System | -Social experience as personas with different genders, sexualities, and races live in late 60s and early 70s
Inspired by true history |  | The user will be able to change their persona. | Persona Change System | -Intereacting with late 60s and early 70s social activists
|  | The user will be able to experience verying intereaction based on their selected persona | Friendly VR User Interface | -Wondering freely around the U of I Quad in late 60s and early 70s
|  | The user will be able to experience interactions which are strong (potentially abusive), loud, mostly one directional and purely verbal. | NUC Intereaction System
|  | User can have an immersive audio effect to feel being present | NUC AI
Feedback System
| IP/World (high level descriptions) |  | Audio and Voice Acting System
U of I quad in 1960s-70s
User Types (prioritized)
Students
Teachers
Historians